## Workplan
Code | Activity or budget line | Objective | Deliverables | Quantity | Unit cost (KES) | Amount (KES) | Quarters | Responsible officer
2211300 | Network support visits to constituency offices | Keep every constituency office connected to the Board network | Visit report per office; faults logged and closed | 24 | 35000 |  | Q1,Q2,Q3,Q4 | Manager, Network Services
3111002 | Replace end-of-life laptops | Equip officers with working, supported computers | 40 laptops issued, asset-tagged and registered | 40 | 95000 |  | Q2 | Principal ICT Officer, Hardware
2210799 | Cyber security awareness training for staff | Reduce phishing and data-handling incidents | 300 officers trained; attendance and test results | 6 | 180000 |  | Q2,Q3 | Senior ICT Officer, Security
2211306 | ICT policy and standards review | Bring ICT policies in line with the Data Protection Act |  |  |  | 850000 | Q3 | Head of ICT

## About this file
NG-CDF FAPM: practice workplan and budget, ICT, FY 2026/27
For the end-to-end practice in FAPM-First-Activity-Practice-Guide.pdf (Part 4). Figures are made up for practice.
Import it in Workplan and budget > Prepare the workplan > Import from template. It gives 4 lines, KES 6,570,000.00.
The last line has no deliverables on purpose: the CEO returns the workplan asking for them (Part 5).
The practice memo is charged to line 2211300, Network support visits to constituency offices.