## Workplan
Code | Activity or budget line | Objective | Deliverables | Quantity | Unit cost (KES) | Amount (KES) | Quarters | Responsible officer
2211300 | Network support visits to constituency offices | Keep every constituency office connected to the Board network | Visit report per office; faults logged and closed | 48 | 35000 |  | Q1,Q2,Q3,Q4 | Manager, Network Services
3111002 | Replace end-of-life laptops | Equip officers with working, supported computers | 40 laptops issued, asset-tagged and registered | 40 | 95000 |  | Q2 | Principal ICT Officer, Hardware
2211306 | Annual software licences and subscriptions | Keep office, security and database software licensed | Licences renewed before expiry; licence register updated | 1 | 6200000 |  | Q1 | Manager, Systems
2210799 | Cyber security awareness training for staff | Reduce phishing and data-handling incidents | 300 officers trained; attendance and test results | 6 | 180000 |  | Q2,Q3 | Senior ICT Officer, Security
2211399 | Data centre and disaster recovery drill | Prove the Board can restore its systems after an outage | Drill report with recovery times; actions closed | 2 | 450000 |  | Q2,Q4 | Manager, Systems
2210303 | Smart NG-CDF rollout support, regional workshops | Help constituency offices use the Smart platform | 10 regional workshops; users trained per office | 10 | 520000 |  | Q1,Q2,Q3 | Head of ICT
2211101 | Internet connectivity, headquarters and regions | Reliable, redundant internet for every office | Monthly availability above 99 percent | 12 | 410000 |  | Q1,Q2,Q3,Q4 | Manager, Network Services
3111111 | Upgrade headquarters Wi-Fi access points | Cover all floors with secure wireless | 24 access points installed and tested | 24 | 68000 |  | Q3 | Senior ICT Officer, Networks
2211306 | ICT policy and standards review | Bring ICT policies in line with the Data Protection Act | Approved ICT policy and standards documents |  |  | 850000 | Q3 | Head of ICT
2210502 | ICT monitoring and evaluation field visits | Check ICT assets and use at constituency offices | Quarterly asset and usage report | 4 | 300000 |  | Q1,Q2,Q3,Q4 | Principal ICT Officer, M&E

## About this example
NG-CDF FAPM: example workplan and budget, ICT, FY 2026/27
An example of a filled-in workplan template. Figures are illustrative, not an approved budget.
How to use it in FAPM: Workplan and budget > Prepare the workplan (FY 2026/27) > Import from template, then choose this file.
Each row becomes one line: the activity, its objective and deliverables, the quarters it runs in and who is responsible.
Amount (KES) may be left empty: FAPM works it out as Quantity x Unit cost. Give the amount when there is no unit (row 10).
Quarters follow the July to June financial year: Q1 Jul to Sep, Q2 Oct to Dec, Q3 Jan to Mar, Q4 Apr to Jun.
After importing, check the lines, add the objectives for the year, and press Submit to the CEO.
Only the first sheet is read. The template itself is downloaded from Workplan and budget > Workplan template.